## Backlog
Key | Type | Epic | Summary | Description | Priority | Status | Resources / References
RT-EP-01 | EPIC | RT-EP-01 | Passive Reconnaissance & Signal Intelligence | Understand the target VLF environment through 100% passive observation before touching anything. Zero emissions phase. | High | To Do | MITRE ATT&CK ICS T0842; ITU Radio Regulations Article 15; GNU Radio Project (gnuradio.org); SDR# (airspy.com/sdrsharp)
RT-1 | STORY | RT-EP-01 | Identify VLF transmissions and map network topology | As a Red Team Operator, I want to identify VLF transmissions in the target environment so I can map the network topology and node count before active testing. | High | To Do | KiwiSDR WebSDR (kiwisdr.com); gqrx.dk; SIGIDWIKI (sigidwiki.com); VLF/LF frequency reference: vlf.it
RT-2 | TASK | RT-EP-01 | Deploy SDR + VLF upconverter for passive spectrum monitoring | Install RTL-SDR v3 or KiwiSDR with Ham-It-Up or SpyVerter upconverter. Set center freq to 125 kHz (accounting for upconverter LO offset). Validate noise floor with known VLF beacon (WWVB 60 kHz). | High | To Do | RTL-SDR Blog (rtl-sdr.com); Ham-It-Up upconverter (nooelec.com); SpyVerter (airspy.com); KiwiSDR (rx.linkfanel.net); GQRX config guide (gqrx.dk/doc/practical-tricks-and-tips)
RT-3 | TASK | RT-EP-01 | Capture and log VLF signal bursts over 72-hour baseline | Run continuous IQ recording using rtl_sdr or GNU Radio file sink at 250 kSps for minimum 72 hours. Timestamp all captures in UTC. Apply 50/60 Hz notch filter. Store as complex float32 IQ files. | High | To Do | GNU Radio file sink documentation (wiki.gnuradio.org); rtl_sdr CLI reference (osmocom.org/trac/wiki/rtl-sdr); SigROK / PulseView for signal logging (sigrok.org)
RT-4 | TASK | RT-EP-01 | Analyze signal timing, modulation type, and duty cycle | Use Inspectrum and URH to characterize each observed signal. Extract: modulation (OOK/FSK/MSK/BPSK), symbol rate, burst duration, inter-burst interval, carrier frequency to ±0.1 Hz. | High | To Do | Inspectrum (github.com/miek/inspectrum); Universal Radio Hacker (github.com/jopohl/urh); URH docs (urh.readthedocs.io); Inspectrum tutorial (github.com/miek/inspectrum/wiki)
RT-5 | TASK | RT-EP-01 | Correlate transmission timing with operational schedules | Cross-reference observed TX bursts with facility shift schedules, environmental events, and known operational patterns. Predictable windows reveal mesh heartbeat intervals and active node roster. | Medium | To Do | MITRE ATT&CK ICS T0842 Network Sniffing; Wireshark / tshark for logging; Python pandas time-series correlation
RT-6 | STORY | RT-EP-01 | Geolocate VLF transmitting nodes using TDOA | As an operator, I want to geolocate VLF nodes using Time Difference of Arrival techniques to produce a physical map of the mesh network for targeting prioritization. | Medium | To Do | TDOA theory: Knapp & Carter (1976) IEEE Trans; GNU Radio TDOA tools; SciPy optimize for hyperbolic positioning (scipy.org); White Rabbit timing project (white-rabbit.web.cern.ch)
RT-7 | TASK | RT-EP-01 | Deploy 3-point synchronized antenna array for triangulation | Set up minimum 3 GPS-disciplined receiver stations with sub-microsecond timing sync (White Rabbit or GPS 1PPS). Station separation 500m–2km depending on target range. Use shielded magnetic loop antennas. | Medium | To Do | GPS 1PPS disciplining: u-blox ZED-F9T datasheet; White Rabbit (ohwr.org/project/white-rabbit); Magnetic loop antenna design: on5au.be/VLF_antenna.htm
RT-8 | TASK | RT-EP-01 | TDOA analysis to plot node positions | Process synchronized IQ captures with cross-correlation to extract time delays. Apply hyperbolic intersection solver (scipy.optimize or custom). Plot results on GIS map. Expected accuracy: 50–200m at 2 km range. | Medium | To Do | SciPy optimize.minimize (scipy.org); NetworkX for topology mapping (networkx.org); QGIS for GIS plotting (qgis.org); Python tdoa library (github.com/AlecThomson/tdoa)
RT-EP-02 | EPIC | RT-EP-02 | Protocol Analysis & Vulnerability Research | Reverse engineer how the VLF mesh communicates. Identify modulation, frame structure, authentication weaknesses, and exploitable protocol flaws. | Critical | To Do | MITRE ATT&CK ICS T0830; Universal Radio Hacker docs (urh.readthedocs.io); STANAG 4285 (nato.int); ITU-R M.1798
RT-9 | STORY | RT-EP-02 | Decode VLF mesh protocol stack to identify exploitable weaknesses | As an operator, I want to fully reverse-engineer the protocol stack from physical layer to application layer, identifying any missing authentication, weak CRCs, or injectable command fields. | Critical | To Do | URH Protocol Analyzer (urh.readthedocs.io/en/latest/Protocol-Analysis.html); Scapy custom layers (scapy.readthedocs.io); ETSI TR 102 000 VLF standard reference
RT-10 | TASK | RT-EP-02 | Identify modulation scheme via FFT waterfall analysis | Open IQ captures in GQRX / SDR# / Inspectrum. Examine waterfall for: OOK (on/off bursts), FSK (two discrete freq lines), MSK (smooth continuous phase), BPSK (phase reversals). Document findings per node. | Critical | To Do | Inspectrum (github.com/miek/inspectrum); SDR# waterfall guide (airspy.com/sdrsharp); Modulation recognition theory: SIGIDWIKI (sigidwiki.com); GNU Radio FFT sink block (wiki.gnuradio.org)
RT-11 | TASK | RT-EP-02 | Demodulate captured signals and extract raw bitstream | Configure URH demodulation for identified scheme. Tune symbol rate by examining Inspectrum symbol rate spectrogram. Export clean bitstream to binary file. Verify with known VLF test signals. | Critical | To Do | URH demodulation tutorial (urh.readthedocs.io); GNU Radio clock recovery (wiki.gnuradio.org/index.php/Symbol_Sync); gr-satellites demodulators (github.com/daniestevez/gr-satellites)
RT-12 | TASK | RT-EP-02 | Identify framing: sync words, addresses, payload boundaries | Apply sliding window search across demodulated bitstream to find repeating patterns (sync words). Use URH Protocol Analyzer to label constant vs. variable fields. Identify address bytes, length fields, and CRC location. | Critical | To Do | URH Protocol Analyzer (urh.readthedocs.io); Python bitstring library (github.com/scott-griffiths/bitstring); CRC RevEng tool (reveng.sourceforge.io) for CRC polynomial identification
RT-13 | TASK | RT-EP-02 | Determine whether encryption or authentication is present | Analyze payload entropy (high entropy = possible encryption). Check for sequential predictable fields. Test for HMAC/MAC fields. Most VLF mesh systems lack crypto — document if absent. If present, identify algorithm. | High | To Do | Python scipy.stats.entropy for payload analysis; CyberChef (gchq.github.io/CyberChef) for quick crypto analysis; ENT entropy testing tool (fourmilab.ch/random)
RT-14 | TASK | RT-EP-02 | Match protocol against known VLF standards | Compare frame structure, modulation, and timing against: STANAG 4285, Piccolo Mk2, RTTY/ITA2, DECCA, LoRa PHY. Document match confidence. Unknown protocols proceed to custom reverse engineering track. | High | To Do | STANAG 4285 (nato.int signals); Piccolo decoder (github.com/alexey-lysiuk/piccolo); RTTY decoder: fldigi (w1hkj.com/FldigiHelp/rtty_page.html); SIGIDWIKI protocol index (sigidwiki.com/wiki/Category:VLF)
RT-15 | STORY | RT-EP-02 | Identify authentication weaknesses in mesh node pairing | As an operator, I want to identify whether node pairing and command authorization uses cryptographic authentication, and if so, assess its strength — looking for replay, MITM, and injection opportunities. | Critical | To Do | MITRE ATT&CK ICS T0859 (Valid Accounts); NIST SP 800-82 ICS Security Guide; RF authentication survey: Faria & Vuong 2015 IEEE
RT-16 | TASK | RT-EP-02 | Test for replay attack susceptibility | Capture a valid command packet transmitted by a legitimate node. Wait 30–60 seconds. Retransmit the captured packet verbatim using calibrated SDR TX. Observe target node response for acceptance/rejection. | Critical | To Do | GNU Radio file source + TX chain (wiki.gnuradio.org); HackRF One for replay TX (greatscottgadgets.com/hackrf); URH replay feature (urh.readthedocs.io/en/latest/Sending.html)
RT-17 | TASK | RT-EP-02 | Test for absence of sequence numbering or nonce mechanisms | Analyze 100+ captured packets for sequence number field. Verify if monotonically increasing, timestamp-based, or random. If sequential — replay attack is trivially feasible. If absent — full replay with no countermeasure. | High | To Do | Python pandas for sequence number analysis; URH compare messages view; Wireshark dissector plugin for custom protocol (wiki.wireshark.org/Lua/Dissectors)
RT-18 | TASK | RT-EP-02 | Fuzz edge-case packet structures | Using URH Fuzzing or custom Python, send packets with: max-length payload, zero-length payload, bit-flipped CRC, invalid command bytes, malformed length fields. Monitor target for crashes, resets, or unexpected responses. | High | To Do | URH Fuzzer (urh.readthedocs.io/en/latest/Fuzzing.html); Sulley fuzzing framework (github.com/OpenRCE/sulley); boofuzz (github.com/jtpereyda/boofuzz); American Fuzzy Lop (lcamtuf.coredump.cx/afl)
RT-EP-03 | EPIC | RT-EP-03 | Active Interference & Disruption Testing | Controlled disruption in authorized lab/range environments only. Assess network resilience to targeted interference, measure recovery time, and identify single points of failure. | High | To Do | MITRE ATT&CK ICS T0815 (Denial of Service); FCC 47 CFR § 333 (authorization required); IEC 62443 ICS security standard; NIST SP 800-82r3
RT-19 | STORY | RT-EP-03 | Assess network resilience to targeted interference | As an operator, I want to quantify how the VLF mesh network responds to various interference scenarios — measuring degradation, recovery time, and rerouting behavior — to identify exploitable resilience gaps. | High | To Do | MITRE ATT&CK ICS T0815; IEEE 802 mesh resilience standards; RF interference measurement: ITU-R SM.2096; MIL-STD-461 EMI testing
RT-20 | TASK | RT-EP-03 | Identify minimum effective jamming power for spot-frequency DoS | In shielded test environment: incrementally increase TX power on target channel. Monitor target node TX cessation. Document JSR (Jamming-to-Signal Ratio) required for communication failure. Typical target: JSR > 10 dB. | High | To Do | GNU Radio signal generator (wiki.gnuradio.org); USRP B210 (ettus.com); Anritsu spectrum analyzer for measurement; ITU-R SM.2096 interference measurement methodology
RT-21 | TASK | RT-EP-03 | Compare swept vs. narrowband jamming effectiveness | Test three jamming modes against mesh: (1) spot CW on channel, (2) swept across band at 1 kHz/s, (3) barrage noise across full VLF band. Measure packet loss rate and recovery time for each. Document power consumption per mode. | Medium | To Do | GNU Radio signal generator blocks; USRP B210 TX; Iperf-style throughput measurement for comparison; MIL-HDBK-235 RF interference handbook
RT-22 | TASK | RT-EP-03 | Assess mesh re-routing behavior under interference | During controlled jamming of one node's channel: observe whether remaining mesh nodes reroute traffic. Time the rerouting convergence. Identify if routing protocol is proactive (pre-computed) or reactive (on-demand). | High | To Do | NetworkX graph analysis (networkx.org); GNU Radio packet counter; OLSR routing protocol reference (RFC 3626); AODV routing reference (RFC 3561)
RT-23 | TASK | RT-EP-03 | Document time-to-recovery for each disruption scenario | For each interference test: record T_start (jamming begins), T_silence (last valid packet), T_resume (first packet post-jam), T_stable (consistent traffic restored). Calculate MTTR per scenario. Document in structured test log. | Medium | To Do | Python time + gnuradio for automated measurement; pandas for MTTR statistics; Test log template: NIST SP 800-115 Appendix D
RT-24 | STORY | RT-EP-03 | Test node isolation attacks to sever mesh segments | As an operator, I want to surgically isolate specific mesh segments by targeting only relay nodes with the highest betweenness centrality — causing a network partition while minimizing observable RF footprint. | High | To Do | NetworkX betweenness centrality (networkx.org/documentation); MITRE ATT&CK ICS T0828 (Loss of View); Graph partitioning algorithms: scipy.sparse.csgraph
RT-25 | TASK | RT-EP-03 | Craft malformed packets to trigger node crash/reset | Send packets with: overlapping length fields, recursive routing headers, maximum repeated retransmission requests, CRC=0x0000, and cmd=0xFF (typically reserved). Monitor for node TX cessation indicating firmware crash or watchdog reset. | High | To Do | Scapy for packet crafting (scapy.readthedocs.io); URH fuzzer; HackRF One for TX; Logic analyzer or second SDR to detect node reboot signature
RT-26 | TASK | RT-EP-03 | Test selective node targeting vs. broadcast disruption | Compare impact of: (A) targeted unicast malformed packets to one node address vs. (B) broadcast malformed packets. Measure disruption to non-targeted nodes in each case. Document collateral impact radius. | Medium | To Do | Scapy custom VLF layer; GNU Radio multi-channel monitor; MITRE ATT&CK ICS T0826 (Loss of Availability)
RT-27 | TASK | RT-EP-03 | Attempt to induce network partition via routing manipulation | If routing protocol identified: craft and inject poisoned routing updates that cause nodes to drop valid relay paths. Inspired by BGP route poisoning. Monitor for isolated node segments unable to communicate with mesh gateway. | High | To Do | BGP route poisoning analogy: RFC 4272 (BGP security); OLSR route injection research (Adjih et al. 2003); Scapy routing packet crafting; NetworkX partition detection
RT-EP-04 | EPIC | RT-EP-04 | Injection & Spoofing | Active exploitation phase: inject crafted VLF packets to issue unauthorized commands, spoof node identities, and attempt man-in-the-middle positioning within the mesh relay chain. | Critical | To Do | MITRE ATT&CK ICS T0856 (Spoof Reporting Message); T0830 (Man in the Middle); Scapy (scapy.readthedocs.io); 47 USC § 333 — written authorization required
RT-28 | STORY | RT-EP-04 | Inject crafted VLF packets to spoof legitimate node traffic | As an operator, I want to craft and transmit VLF packets that appear to originate from legitimate mesh nodes — using reconstructed protocol knowledge — to issue unauthorized commands to downstream nodes. | Critical | To Do | Scapy packet crafting (scapy.readthedocs.io); HackRF / USRP B210 for TX; MITRE ATT&CK ICS T0856; GNU Radio modulation blocks (wiki.gnuradio.org)
RT-29 | TASK | RT-EP-04 | Source/build VLF transmitter capable of signal injection | Options: (A) HackRF One + PA + LPF for 3–30 kHz (requires upconverter in reverse), (B) USRP B210 with daughterboard, (C) direct digital synthesis with AD9851/AD9833 for simple modulations. Calibrate output against reference receiver. | Critical | To Do | HackRF One (greatscottgadgets.com/hackrf); USRP B210 (ettus.com/products/details/UB210-KIT); AD9851 DDS (analog.com); GNU Radio TX chain tutorial (wiki.gnuradio.org/index.php/Tutorials)
RT-30 | TASK | RT-EP-04 | Reconstruct valid packet format from protocol RE | Using findings from RT-EP-02: implement complete packet builder in Python/Scapy. Include: correct sync word, src/dst address fields, sequence number prediction, command byte, payload, and valid CRC. Validate against captured real packets. | Critical | To Do | Scapy custom layer docs (scapy.readthedocs.io/en/latest/build_dissect.html); CRC RevEng (reveng.sourceforge.io); Python crcmod library (crcmod.sourceforge.net); pwntools for binary crafting (docs.pwntools.com)
RT-31 | TASK | RT-EP-04 | Inject spoofed command packets and observe node behavior | Transmit crafted command packets during target node's expected TX window to minimize collision probability. Start with benign commands (status request, ACK). Monitor downstream response via passive SDR. Escalate to control commands only with explicit RoE authorization. | Critical | To Do | GNU Radio TX flowgraph; USRP B210; MITRE ATT&CK ICS T0855 (Unauthorized Command Message); IEC 62443-3-3 system security requirements
RT-32 | TASK | RT-EP-04 | Test for routing table injection (route poisoning) | If mesh uses a routing protocol (OLSR, AODV, or proprietary): craft routing update packets with manipulated topology advertisements. Goal: redirect traffic through an operator-controlled relay node for passive interception. | High | To Do | OLSR RFC 3626 (rfc-editor.org/rfc/rfc3626); AODV RFC 3561; BGP poisoning analogy RFC 4272; Scapy OLSR/routing packet crafting
RT-33 | STORY | RT-EP-04 | Impersonate trusted mesh node to intercept relayed traffic | As an operator, I want to fully impersonate a trusted mesh node by spoofing its RF identity — allowing me to receive, log, and potentially re-transmit traffic intended for that node. | Critical | To Do | MITRE ATT&CK ICS T0830 (Man in the Middle); GNU Radio relay flowgraph; RF fingerprinting countermeasure research: Brik et al. 2008 MOBICOM
RT-34 | TASK | RT-EP-04 | Perform node identity spoofing using captured address fields | Extract node ID, address bytes, and any hardware identifier fields from captured packets. Construct TX to match exact carrier frequency, modulation parameters, and timing profile of target node. Use rise-time matching for RF fingerprint evasion. | Critical | To Do | GNU Radio modulation blocks; USRP B210 fine frequency control; RF fingerprinting evasion research; Scapy address field manipulation
RT-35 | TASK | RT-EP-04 | Assess whether nodes validate identity before relaying | Transmit spoofed packets from known-invalid node addresses. Verify whether relay nodes forward or silently drop packets from unrecognized sources. Test boundary conditions: valid format, invalid address. Document neighbor table behavior. | High | To Do | Passive SDR monitor for relay confirmation; Wireshark-style packet log comparison; MITRE ATT&CK ICS T0881 (Service Stop)
RT-36 | TASK | RT-EP-04 | Attempt man-in-the-middle relay positioning | Position operator TX/RX between two nodes. Receive from Node A, log, optionally modify, then retransmit to Node B with correct timing. Requires sub-millisecond processing pipeline. GNU Radio provides the relay framework. | Critical | To Do | MITRE ATT&CK ICS T0830; GNU Radio real-time relay flowgraph; USRP B210 full-duplex simultaneous TX/RX; HackRF (half-duplex only — not suitable for simultaneous relay)
RT-EP-05 | EPIC | RT-EP-05 | Reporting & Defensive Recommendations | Produce actionable deliverables: evidence packages, MITRE mappings, executive summary, and technical hardening recommendations aligned to ICS security frameworks. | High | To Do | MITRE ATT&CK for ICS (attack.mitre.org/matrices/ics); NIST SP 800-82r3 ICS Guide; IEC 62443 series; CISA ICS-CERT advisories (cisa.gov/ics)
RT-37 | STORY | RT-EP-05 | Document all findings with reproducible evidence packages | As an operator, I want to compile all raw captures, decoded packets, injection logs, and test results into structured evidence packages that allow findings to be independently verified and reproduced. | High | To Do | NIST SP 800-115 Technical Guide to Information Security Testing; GNU Radio IQ file format documentation; SigMF metadata standard (github.com/sigmf/SigMF) for annotated IQ captures
RT-38 | TASK | RT-EP-05 | Compile signal captures, packets, and injection logs | Organize all IQ captures in SigMF format (signal + metadata JSON). Export URH decoded packet logs as CSV/PCAP. Document injection attempts with timestamps, TX parameters, and observed responses. Hash all evidence files (SHA-256). | High | To Do | SigMF standard (sigmf.github.io); GNU Radio IQ to SigMF converter; Wireshark PCAP format (wireshark.org); Python hashlib for SHA-256 evidence integrity
RT-39 | TASK | RT-EP-05 | Map findings to MITRE ATT&CK for ICS | Map each identified vulnerability and successful attack technique to the MITRE ATT&CK for ICS matrix. Include: tactic, technique ID, sub-technique where applicable, and evidence reference. Use ATT&CK Navigator for visualization. | High | To Do | MITRE ATT&CK for ICS (attack.mitre.org/matrices/ics); ATT&CK Navigator (mitre-attack.github.io/attack-navigator); MITRE ATLAS (atlas.mitre.org); Key techniques: T0842, T0856, T0830, T0815, T0828
RT-40 | TASK | RT-EP-05 | Write executive summary covering operational risk | Produce 2-page executive summary covering: attack surface overview, most critical findings (CVSS-equivalent scoring), operational impact scenarios (what an adversary could actually do), and prioritized risk ranking. Non-technical audience. | High | To Do | CVSS v3.1 scoring (first.org/cvss); NIST SP 800-30 Risk Assessment Guide; SANS Penetration Testing Report template (sans.org); CWE/CVE reference (cwe.mitre.org)
RT-41 | STORY | RT-EP-05 | Provide actionable hardening recommendations | As an operator, I want to deliver concrete, implementable defensive countermeasures for each identified vulnerability — prioritized by feasibility and risk reduction impact. | High | To Do | IEC 62443-3-3 system security requirements; NIST SP 800-82r3 Chapter 6; CISA ICS security baseline (cisa.gov/ics-recommended-practices); NSA/CISA joint guidance on ICS security
RT-42 | TASK | RT-EP-05 | Recommend protocol-layer authentication implementation | Specify HMAC-SHA256 with pre-shared keys as minimum viable authentication for VLF constraints. Detail key management approach (static PSK vs. periodic rotation). Provide sample frame structure modification showing auth field placement. | High | To Do | HMAC RFC 2104 (rfc-editor.org/rfc/rfc2104); NIST SP 800-107 HMAC recommendation; NIST SP 800-57 Key Management; IEC 62443-3-3 SR 1.1 through SR 1.5
RT-43 | TASK | RT-EP-05 | Recommend spread-spectrum / frequency-hopping countermeasures | Specify FHSS implementation approach appropriate for VLF constraints (limited bandwidth requires slow hopping). Recommend DSSS where bandwidth allows. Include FHSS hop sequence generation using PRNG with shared seed as DoS countermeasure. | High | To Do | IEEE 802.15.4 DSSS/FHSS standard; FCC Part 15.247 FHSS requirements; MILSTD-188-141B frequency hopping; NSA/CSS EPL approved frequency hopping implementations
RT-44 | TASK | RT-EP-05 | Recommend anomaly detection baselines for VLF monitoring | Define normal behavior baseline: expected TX nodes, carrier frequencies ±tolerance, burst timing windows, packet rates. Specify anomaly thresholds that should trigger alerts: new node address, out-of-window TX, unexpected carrier, elevated packet rate. | High | To Do | MITRE ATT&CK ICS detection guidance; Dragos ICS anomaly detection whitepaper; Claroty ICS monitoring; SigMF for annotated baseline capture; NIST SP 800-137 continuous monitoring

## Epics Overview
Epic Key | Epic Name | Description | Stories | Tasks | Priority | Status | Key Resources
RT-EP-01 | Passive Reconnaissance & Signal Intelligence | Understand the target VLF environment through 100% passive observation before touching anything. Zero emissions phase. | 2 | 6 | High | To Do | MITRE ATT&CK ICS T0842; ITU Radio Regulations Article 15; GNU Radio Project (gnuradio.org); SDR# (airspy.com/sdrsharp)
RT-EP-02 | Protocol Analysis & Vulnerability Research | Reverse engineer how the VLF mesh communicates. Identify modulation, frame structure, authentication weaknesses, and exploitable protocol flaws. | 2 | 8 | Critical | To Do | MITRE ATT&CK ICS T0830; Universal Radio Hacker docs (urh.readthedocs.io); STANAG 4285 (nato.int); ITU-R M.1798
RT-EP-03 | Active Interference & Disruption Testing | Controlled disruption in authorized lab/range environments only. Assess network resilience to targeted interference, measure recovery time, and identify single points of failure. | 2 | 7 | High | To Do | MITRE ATT&CK ICS T0815 (Denial of Service); FCC 47 CFR § 333 (authorization required); IEC 62443 ICS security standard; NIST SP 800-82r3
RT-EP-04 | Injection & Spoofing | Active exploitation phase: inject crafted VLF packets to issue unauthorized commands, spoof node identities, and attempt man-in-the-middle positioning within the mesh relay chain. | 2 | 7 | Critical | To Do | MITRE ATT&CK ICS T0856 (Spoof Reporting Message); T0830 (Man in the Middle); Scapy (scapy.readthedocs.io); 47 USC § 333 — written authorization required
RT-EP-05 | Reporting & Defensive Recommendations | Produce actionable deliverables: evidence packages, MITRE mappings, executive summary, and technical hardening recommendations aligned to ICS security frameworks. | 2 | 6 | High | To Do | MITRE ATT&CK for ICS (attack.mitre.org/matrices/ics); NIST SP 800-82r3 ICS Guide; IEC 62443 series; CISA ICS-CERT advisories (cisa.gov/ics)

## EP01 — Recon & SIGINT
EPIC: RT-EP-01 // Passive Reconnaissance & Signal Intelligence
Understand the target VLF environment through 100% passive observation before touching anything. Zero emissions phase.
Resources: MITRE ATT&CK ICS T0842; ITU Radio Regulations Article 15; GNU Radio Project (gnuradio.org); SDR# (airspy.com/sdrsharp)
Key | Type | Summary | Description | Priority | Status | Est. Effort | Resources / References
RT-1 | STORY | Identify VLF transmissions and map network topology | As a Red Team Operator, I want to identify VLF transmissions in the target environment so I can map the network topology and node count before active testing. | High | To Do | 3 days | KiwiSDR WebSDR (kiwisdr.com); gqrx.dk; SIGIDWIKI (sigidwiki.com); VLF/LF frequency reference: vlf.it
RT-2 | TASK | Deploy SDR + VLF upconverter for passive spectrum monitoring | Install RTL-SDR v3 or KiwiSDR with Ham-It-Up or SpyVerter upconverter. Set center freq to 125 kHz (accounting for upconverter LO offset). Validate noise floor with known VLF beacon (WWVB 60 kHz). | High | To Do | 1 day | RTL-SDR Blog (rtl-sdr.com); Ham-It-Up upconverter (nooelec.com); SpyVerter (airspy.com); KiwiSDR (rx.linkfanel.net); GQRX config guide (gqrx.dk/doc/practical-tricks-and-tips)
RT-3 | TASK | Capture and log VLF signal bursts over 72-hour baseline | Run continuous IQ recording using rtl_sdr or GNU Radio file sink at 250 kSps for minimum 72 hours. Timestamp all captures in UTC. Apply 50/60 Hz notch filter. Store as complex float32 IQ files. | High | To Do | 1 day | GNU Radio file sink documentation (wiki.gnuradio.org); rtl_sdr CLI reference (osmocom.org/trac/wiki/rtl-sdr); SigROK / PulseView for signal logging (sigrok.org)
RT-4 | TASK | Analyze signal timing, modulation type, and duty cycle | Use Inspectrum and URH to characterize each observed signal. Extract: modulation (OOK/FSK/MSK/BPSK), symbol rate, burst duration, inter-burst interval, carrier frequency to ±0.1 Hz. | High | To Do | 1 day | Inspectrum (github.com/miek/inspectrum); Universal Radio Hacker (github.com/jopohl/urh); URH docs (urh.readthedocs.io); Inspectrum tutorial (github.com/miek/inspectrum/wiki)
RT-5 | TASK | Correlate transmission timing with operational schedules | Cross-reference observed TX bursts with facility shift schedules, environmental events, and known operational patterns. Predictable windows reveal mesh heartbeat intervals and active node roster. | Medium | To Do | 0.5 day | MITRE ATT&CK ICS T0842 Network Sniffing; Wireshark / tshark for logging; Python pandas time-series correlation
RT-6 | STORY | Geolocate VLF transmitting nodes using TDOA | As an operator, I want to geolocate VLF nodes using Time Difference of Arrival techniques to produce a physical map of the mesh network for targeting prioritization. | Medium | To Do | 3 days | TDOA theory: Knapp & Carter (1976) IEEE Trans; GNU Radio TDOA tools; SciPy optimize for hyperbolic positioning (scipy.org); White Rabbit timing project (white-rabbit.web.cern.ch)
RT-7 | TASK | Deploy 3-point synchronized antenna array for triangulation | Set up minimum 3 GPS-disciplined receiver stations with sub-microsecond timing sync (White Rabbit or GPS 1PPS). Station separation 500m–2km depending on target range. Use shielded magnetic loop antennas. | Medium | To Do | 0.5 day | GPS 1PPS disciplining: u-blox ZED-F9T datasheet; White Rabbit (ohwr.org/project/white-rabbit); Magnetic loop antenna design: on5au.be/VLF_antenna.htm
RT-8 | TASK | TDOA analysis to plot node positions | Process synchronized IQ captures with cross-correlation to extract time delays. Apply hyperbolic intersection solver (scipy.optimize or custom). Plot results on GIS map. Expected accuracy: 50–200m at 2 km range. | Medium | To Do | 0.5 day | SciPy optimize.minimize (scipy.org); NetworkX for topology mapping (networkx.org); QGIS for GIS plotting (qgis.org); Python tdoa library (github.com/AlecThomson/tdoa)

## EP02 — Protocol Analysis
EPIC: RT-EP-02 // Protocol Analysis & Vulnerability Research
Reverse engineer how the VLF mesh communicates. Identify modulation, frame structure, authentication weaknesses, and exploitable protocol flaws.
Resources: MITRE ATT&CK ICS T0830; Universal Radio Hacker docs (urh.readthedocs.io); STANAG 4285 (nato.int); ITU-R M.1798
Key | Type | Summary | Description | Priority | Status | Est. Effort | Resources / References
RT-9 | STORY | Decode VLF mesh protocol stack to identify exploitable weaknesses | As an operator, I want to fully reverse-engineer the protocol stack from physical layer to application layer, identifying any missing authentication, weak CRCs, or injectable command fields. | Critical | To Do | 3 days | URH Protocol Analyzer (urh.readthedocs.io/en/latest/Protocol-Analysis.html); Scapy custom layers (scapy.readthedocs.io); ETSI TR 102 000 VLF standard reference
RT-10 | TASK | Identify modulation scheme via FFT waterfall analysis | Open IQ captures in GQRX / SDR# / Inspectrum. Examine waterfall for: OOK (on/off bursts), FSK (two discrete freq lines), MSK (smooth continuous phase), BPSK (phase reversals). Document findings per node. | Critical | To Do | 1 day | Inspectrum (github.com/miek/inspectrum); SDR# waterfall guide (airspy.com/sdrsharp); Modulation recognition theory: SIGIDWIKI (sigidwiki.com); GNU Radio FFT sink block (wiki.gnuradio.org)
RT-11 | TASK | Demodulate captured signals and extract raw bitstream | Configure URH demodulation for identified scheme. Tune symbol rate by examining Inspectrum symbol rate spectrogram. Export clean bitstream to binary file. Verify with known VLF test signals. | Critical | To Do | 1 day | URH demodulation tutorial (urh.readthedocs.io); GNU Radio clock recovery (wiki.gnuradio.org/index.php/Symbol_Sync); gr-satellites demodulators (github.com/daniestevez/gr-satellites)
RT-12 | TASK | Identify framing: sync words, addresses, payload boundaries | Apply sliding window search across demodulated bitstream to find repeating patterns (sync words). Use URH Protocol Analyzer to label constant vs. variable fields. Identify address bytes, length fields, and CRC location. | Critical | To Do | 1 day | URH Protocol Analyzer (urh.readthedocs.io); Python bitstring library (github.com/scott-griffiths/bitstring); CRC RevEng tool (reveng.sourceforge.io) for CRC polynomial identification
RT-13 | TASK | Determine whether encryption or authentication is present | Analyze payload entropy (high entropy = possible encryption). Check for sequential predictable fields. Test for HMAC/MAC fields. Most VLF mesh systems lack crypto — document if absent. If present, identify algorithm. | High | To Do | 1 day | Python scipy.stats.entropy for payload analysis; CyberChef (gchq.github.io/CyberChef) for quick crypto analysis; ENT entropy testing tool (fourmilab.ch/random)
RT-14 | TASK | Match protocol against known VLF standards | Compare frame structure, modulation, and timing against: STANAG 4285, Piccolo Mk2, RTTY/ITA2, DECCA, LoRa PHY. Document match confidence. Unknown protocols proceed to custom reverse engineering track. | High | To Do | 1 day | STANAG 4285 (nato.int signals); Piccolo decoder (github.com/alexey-lysiuk/piccolo); RTTY decoder: fldigi (w1hkj.com/FldigiHelp/rtty_page.html); SIGIDWIKI protocol index (sigidwiki.com/wiki/Category:VLF)
RT-15 | STORY | Identify authentication weaknesses in mesh node pairing | As an operator, I want to identify whether node pairing and command authorization uses cryptographic authentication, and if so, assess its strength — looking for replay, MITM, and injection opportunities. | Critical | To Do | 3 days | MITRE ATT&CK ICS T0859 (Valid Accounts); NIST SP 800-82 ICS Security Guide; RF authentication survey: Faria & Vuong 2015 IEEE
RT-16 | TASK | Test for replay attack susceptibility | Capture a valid command packet transmitted by a legitimate node. Wait 30–60 seconds. Retransmit the captured packet verbatim using calibrated SDR TX. Observe target node response for acceptance/rejection. | Critical | To Do | 1 day | GNU Radio file source + TX chain (wiki.gnuradio.org); HackRF One for replay TX (greatscottgadgets.com/hackrf); URH replay feature (urh.readthedocs.io/en/latest/Sending.html)
RT-17 | TASK | Test for absence of sequence numbering or nonce mechanisms | Analyze 100+ captured packets for sequence number field. Verify if monotonically increasing, timestamp-based, or random. If sequential — replay attack is trivially feasible. If absent — full replay with no countermeasure. | High | To Do | 1 day | Python pandas for sequence number analysis; URH compare messages view; Wireshark dissector plugin for custom protocol (wiki.wireshark.org/Lua/Dissectors)
RT-18 | TASK | Fuzz edge-case packet structures | Using URH Fuzzing or custom Python, send packets with: max-length payload, zero-length payload, bit-flipped CRC, invalid command bytes, malformed length fields. Monitor target for crashes, resets, or unexpected responses. | High | To Do | 1 day | URH Fuzzer (urh.readthedocs.io/en/latest/Fuzzing.html); Sulley fuzzing framework (github.com/OpenRCE/sulley); boofuzz (github.com/jtpereyda/boofuzz); American Fuzzy Lop (lcamtuf.coredump.cx/afl)

## EP03 — Interference Ops
EPIC: RT-EP-03 // Active Interference & Disruption Testing
Controlled disruption in authorized lab/range environments only. Assess network resilience to targeted interference, measure recovery time, and identify single points of failure.
Resources: MITRE ATT&CK ICS T0815 (Denial of Service); FCC 47 CFR § 333 (authorization required); IEC 62443 ICS security standard; NIST SP 800-82r3
Key | Type | Summary | Description | Priority | Status | Est. Effort | Resources / References
RT-19 | STORY | Assess network resilience to targeted interference | As an operator, I want to quantify how the VLF mesh network responds to various interference scenarios — measuring degradation, recovery time, and rerouting behavior — to identify exploitable resilience gaps. | High | To Do | 3 days | MITRE ATT&CK ICS T0815; IEEE 802 mesh resilience standards; RF interference measurement: ITU-R SM.2096; MIL-STD-461 EMI testing
RT-20 | TASK | Identify minimum effective jamming power for spot-frequency DoS | In shielded test environment: incrementally increase TX power on target channel. Monitor target node TX cessation. Document JSR (Jamming-to-Signal Ratio) required for communication failure. Typical target: JSR > 10 dB. | High | To Do | 1 day | GNU Radio signal generator (wiki.gnuradio.org); USRP B210 (ettus.com); Anritsu spectrum analyzer for measurement; ITU-R SM.2096 interference measurement methodology
RT-21 | TASK | Compare swept vs. narrowband jamming effectiveness | Test three jamming modes against mesh: (1) spot CW on channel, (2) swept across band at 1 kHz/s, (3) barrage noise across full VLF band. Measure packet loss rate and recovery time for each. Document power consumption per mode. | Medium | To Do | 0.5 day | GNU Radio signal generator blocks; USRP B210 TX; Iperf-style throughput measurement for comparison; MIL-HDBK-235 RF interference handbook
RT-22 | TASK | Assess mesh re-routing behavior under interference | During controlled jamming of one node's channel: observe whether remaining mesh nodes reroute traffic. Time the rerouting convergence. Identify if routing protocol is proactive (pre-computed) or reactive (on-demand). | High | To Do | 1 day | NetworkX graph analysis (networkx.org); GNU Radio packet counter; OLSR routing protocol reference (RFC 3626); AODV routing reference (RFC 3561)
RT-23 | TASK | Document time-to-recovery for each disruption scenario | For each interference test: record T_start (jamming begins), T_silence (last valid packet), T_resume (first packet post-jam), T_stable (consistent traffic restored). Calculate MTTR per scenario. Document in structured test log. | Medium | To Do | 0.5 day | Python time + gnuradio for automated measurement; pandas for MTTR statistics; Test log template: NIST SP 800-115 Appendix D
RT-24 | STORY | Test node isolation attacks to sever mesh segments | As an operator, I want to surgically isolate specific mesh segments by targeting only relay nodes with the highest betweenness centrality — causing a network partition while minimizing observable RF footprint. | High | To Do | 3 days | NetworkX betweenness centrality (networkx.org/documentation); MITRE ATT&CK ICS T0828 (Loss of View); Graph partitioning algorithms: scipy.sparse.csgraph
RT-25 | TASK | Craft malformed packets to trigger node crash/reset | Send packets with: overlapping length fields, recursive routing headers, maximum repeated retransmission requests, CRC=0x0000, and cmd=0xFF (typically reserved). Monitor for node TX cessation indicating firmware crash or watchdog reset. | High | To Do | 1 day | Scapy for packet crafting (scapy.readthedocs.io); URH fuzzer; HackRF One for TX; Logic analyzer or second SDR to detect node reboot signature
RT-26 | TASK | Test selective node targeting vs. broadcast disruption | Compare impact of: (A) targeted unicast malformed packets to one node address vs. (B) broadcast malformed packets. Measure disruption to non-targeted nodes in each case. Document collateral impact radius. | Medium | To Do | 0.5 day | Scapy custom VLF layer; GNU Radio multi-channel monitor; MITRE ATT&CK ICS T0826 (Loss of Availability)
RT-27 | TASK | Attempt to induce network partition via routing manipulation | If routing protocol identified: craft and inject poisoned routing updates that cause nodes to drop valid relay paths. Inspired by BGP route poisoning. Monitor for isolated node segments unable to communicate with mesh gateway. | High | To Do | 1 day | BGP route poisoning analogy: RFC 4272 (BGP security); OLSR route injection research (Adjih et al. 2003); Scapy routing packet crafting; NetworkX partition detection

## EP04 — Injection & Spoofing
EPIC: RT-EP-04 // Injection & Spoofing
Active exploitation phase: inject crafted VLF packets to issue unauthorized commands, spoof node identities, and attempt man-in-the-middle positioning within the mesh relay chain.
Resources: MITRE ATT&CK ICS T0856 (Spoof Reporting Message); T0830 (Man in the Middle); Scapy (scapy.readthedocs.io); 47 USC § 333 — written authorization required
Key | Type | Summary | Description | Priority | Status | Est. Effort | Resources / References
RT-28 | STORY | Inject crafted VLF packets to spoof legitimate node traffic | As an operator, I want to craft and transmit VLF packets that appear to originate from legitimate mesh nodes — using reconstructed protocol knowledge — to issue unauthorized commands to downstream nodes. | Critical | To Do | 3 days | Scapy packet crafting (scapy.readthedocs.io); HackRF / USRP B210 for TX; MITRE ATT&CK ICS T0856; GNU Radio modulation blocks (wiki.gnuradio.org)
RT-29 | TASK | Source/build VLF transmitter capable of signal injection | Options: (A) HackRF One + PA + LPF for 3–30 kHz (requires upconverter in reverse), (B) USRP B210 with daughterboard, (C) direct digital synthesis with AD9851/AD9833 for simple modulations. Calibrate output against reference receiver. | Critical | To Do | 1 day | HackRF One (greatscottgadgets.com/hackrf); USRP B210 (ettus.com/products/details/UB210-KIT); AD9851 DDS (analog.com); GNU Radio TX chain tutorial (wiki.gnuradio.org/index.php/Tutorials)
RT-30 | TASK | Reconstruct valid packet format from protocol RE | Using findings from RT-EP-02: implement complete packet builder in Python/Scapy. Include: correct sync word, src/dst address fields, sequence number prediction, command byte, payload, and valid CRC. Validate against captured real packets. | Critical | To Do | 1 day | Scapy custom layer docs (scapy.readthedocs.io/en/latest/build_dissect.html); CRC RevEng (reveng.sourceforge.io); Python crcmod library (crcmod.sourceforge.net); pwntools for binary crafting (docs.pwntools.com)
RT-31 | TASK | Inject spoofed command packets and observe node behavior | Transmit crafted command packets during target node's expected TX window to minimize collision probability. Start with benign commands (status request, ACK). Monitor downstream response via passive SDR. Escalate to control commands only with explicit RoE authorization. | Critical | To Do | 1 day | GNU Radio TX flowgraph; USRP B210; MITRE ATT&CK ICS T0855 (Unauthorized Command Message); IEC 62443-3-3 system security requirements
RT-32 | TASK | Test for routing table injection (route poisoning) | If mesh uses a routing protocol (OLSR, AODV, or proprietary): craft routing update packets with manipulated topology advertisements. Goal: redirect traffic through an operator-controlled relay node for passive interception. | High | To Do | 1 day | OLSR RFC 3626 (rfc-editor.org/rfc/rfc3626); AODV RFC 3561; BGP poisoning analogy RFC 4272; Scapy OLSR/routing packet crafting
RT-33 | STORY | Impersonate trusted mesh node to intercept relayed traffic | As an operator, I want to fully impersonate a trusted mesh node by spoofing its RF identity — allowing me to receive, log, and potentially re-transmit traffic intended for that node. | Critical | To Do | 3 days | MITRE ATT&CK ICS T0830 (Man in the Middle); GNU Radio relay flowgraph; RF fingerprinting countermeasure research: Brik et al. 2008 MOBICOM
RT-34 | TASK | Perform node identity spoofing using captured address fields | Extract node ID, address bytes, and any hardware identifier fields from captured packets. Construct TX to match exact carrier frequency, modulation parameters, and timing profile of target node. Use rise-time matching for RF fingerprint evasion. | Critical | To Do | 1 day | GNU Radio modulation blocks; USRP B210 fine frequency control; RF fingerprinting evasion research; Scapy address field manipulation
RT-35 | TASK | Assess whether nodes validate identity before relaying | Transmit spoofed packets from known-invalid node addresses. Verify whether relay nodes forward or silently drop packets from unrecognized sources. Test boundary conditions: valid format, invalid address. Document neighbor table behavior. | High | To Do | 1 day | Passive SDR monitor for relay confirmation; Wireshark-style packet log comparison; MITRE ATT&CK ICS T0881 (Service Stop)
RT-36 | TASK | Attempt man-in-the-middle relay positioning | Position operator TX/RX between two nodes. Receive from Node A, log, optionally modify, then retransmit to Node B with correct timing. Requires sub-millisecond processing pipeline. GNU Radio provides the relay framework. | Critical | To Do | 1 day | MITRE ATT&CK ICS T0830; GNU Radio real-time relay flowgraph; USRP B210 full-duplex simultaneous TX/RX; HackRF (half-duplex only — not suitable for simultaneous relay)

## EP05 — Reporting
EPIC: RT-EP-05 // Reporting & Defensive Recommendations
Produce actionable deliverables: evidence packages, MITRE mappings, executive summary, and technical hardening recommendations aligned to ICS security frameworks.
Resources: MITRE ATT&CK for ICS (attack.mitre.org/matrices/ics); NIST SP 800-82r3 ICS Guide; IEC 62443 series; CISA ICS-CERT advisories (cisa.gov/ics)
Key | Type | Summary | Description | Priority | Status | Est. Effort | Resources / References
RT-37 | STORY | Document all findings with reproducible evidence packages | As an operator, I want to compile all raw captures, decoded packets, injection logs, and test results into structured evidence packages that allow findings to be independently verified and reproduced. | High | To Do | 3 days | NIST SP 800-115 Technical Guide to Information Security Testing; GNU Radio IQ file format documentation; SigMF metadata standard (github.com/sigmf/SigMF) for annotated IQ captures
RT-38 | TASK | Compile signal captures, packets, and injection logs | Organize all IQ captures in SigMF format (signal + metadata JSON). Export URH decoded packet logs as CSV/PCAP. Document injection attempts with timestamps, TX parameters, and observed responses. Hash all evidence files (SHA-256). | High | To Do | 1 day | SigMF standard (sigmf.github.io); GNU Radio IQ to SigMF converter; Wireshark PCAP format (wireshark.org); Python hashlib for SHA-256 evidence integrity
RT-39 | TASK | Map findings to MITRE ATT&CK for ICS | Map each identified vulnerability and successful attack technique to the MITRE ATT&CK for ICS matrix. Include: tactic, technique ID, sub-technique where applicable, and evidence reference. Use ATT&CK Navigator for visualization. | High | To Do | 1 day | MITRE ATT&CK for ICS (attack.mitre.org/matrices/ics); ATT&CK Navigator (mitre-attack.github.io/attack-navigator); MITRE ATLAS (atlas.mitre.org); Key techniques: T0842, T0856, T0830, T0815, T0828
RT-40 | TASK | Write executive summary covering operational risk | Produce 2-page executive summary covering: attack surface overview, most critical findings (CVSS-equivalent scoring), operational impact scenarios (what an adversary could actually do), and prioritized risk ranking. Non-technical audience. | High | To Do | 1 day | CVSS v3.1 scoring (first.org/cvss); NIST SP 800-30 Risk Assessment Guide; SANS Penetration Testing Report template (sans.org); CWE/CVE reference (cwe.mitre.org)
RT-41 | STORY | Provide actionable hardening recommendations | As an operator, I want to deliver concrete, implementable defensive countermeasures for each identified vulnerability — prioritized by feasibility and risk reduction impact. | High | To Do | 3 days | IEC 62443-3-3 system security requirements; NIST SP 800-82r3 Chapter 6; CISA ICS security baseline (cisa.gov/ics-recommended-practices); NSA/CISA joint guidance on ICS security
RT-42 | TASK | Recommend protocol-layer authentication implementation | Specify HMAC-SHA256 with pre-shared keys as minimum viable authentication for VLF constraints. Detail key management approach (static PSK vs. periodic rotation). Provide sample frame structure modification showing auth field placement. | High | To Do | 1 day | HMAC RFC 2104 (rfc-editor.org/rfc/rfc2104); NIST SP 800-107 HMAC recommendation; NIST SP 800-57 Key Management; IEC 62443-3-3 SR 1.1 through SR 1.5
RT-43 | TASK | Recommend spread-spectrum / frequency-hopping countermeasures | Specify FHSS implementation approach appropriate for VLF constraints (limited bandwidth requires slow hopping). Recommend DSSS where bandwidth allows. Include FHSS hop sequence generation using PRNG with shared seed as DoS countermeasure. | High | To Do | 1 day | IEEE 802.15.4 DSSS/FHSS standard; FCC Part 15.247 FHSS requirements; MILSTD-188-141B frequency hopping; NSA/CSS EPL approved frequency hopping implementations
RT-44 | TASK | Recommend anomaly detection baselines for VLF monitoring | Define normal behavior baseline: expected TX nodes, carrier frequencies ±tolerance, burst timing windows, packet rates. Specify anomaly thresholds that should trigger alerts: new node address, out-of-window TX, unexpected carrier, elevated packet rate. | High | To Do | 1 day | MITRE ATT&CK ICS detection guidance; Dragos ICS anomaly detection whitepaper; Claroty ICS monitoring; SigMF for annotated baseline capture; NIST SP 800-137 continuous monitoring

## Resources Master
VLF RED TEAM — MASTER RESOURCE & TOOL REFERENCE
Category | Tool / Resource | Purpose | URL / Reference
SDR Hardware | RTL-SDR v3 | Entry-level passive VLF monitoring (needs upconverter) | rtl-sdr.com
SDR Hardware | KiwiSDR | Best-in-class 0–30 MHz coverage, native VLF, network-connected | rx.linkfanel.net / kiwisdr.com
SDR Hardware | Perseus SDR | Professional 120 dB dynamic range VLF receiver | microtelecom.it/perseus
SDR Hardware | HackRF One | Half-duplex TX/RX 1 MHz–6 GHz, needs upconverter for VLF | greatscottgadgets.com/hackrf
SDR Hardware | USRP B210 | Full-duplex professional TX/RX, preferred for active ops | ettus.com/products/details/UB210-KIT
SDR Hardware | LimeSDR | Budget full-duplex alternative to USRP | limemicro.com/products/boards/limesdr
Upconverters | Ham-It-Up v1.3 | Shifts VLF (0–50 MHz) up for RTL-SDR reception | nooelec.com
Upconverters | SpyVerter R2 | High-quality upconverter, pairs with AirSpy SDR | airspy.com/spyverter-r2
Software — Passive | GQRX | GUI SDR receiver, waterfall, VLF monitoring | gqrx.dk
Software — Passive | SDR# | Windows SDR GUI, plugin ecosystem | airspy.com/sdrsharp
Software — Passive | Inspectrum | Symbol rate analysis, IQ file examination | github.com/miek/inspectrum
Software — Passive | Universal Radio Hacker (URH) | End-to-end protocol RE: demod, analysis, fuzzing, TX | github.com/jopohl/urh
Software — Active | GNU Radio | Signal processing framework for custom TX/RX chains | gnuradio.org
Software — Active | gr-osmosdr | GNU Radio source/sink for RTL-SDR, HackRF, USRP | osmocom.org/projects/gr-osmosdr
Software — Active | gr-satellites | Collection of demodulators including VLF-adjacent | github.com/daniestevez/gr-satellites
Packet Crafting | Scapy | Python packet crafting library, custom protocol layers | scapy.readthedocs.io
Packet Crafting | pwntools | Binary exploitation and packet crafting framework | docs.pwntools.com
Packet Crafting | CRC RevEng | Identify unknown CRC polynomials from sample data | reveng.sourceforge.io
Packet Crafting | CyberChef | Browser-based encoding/decoding/crypto analysis | gchq.github.io/CyberChef
Protocol Analysis | SigMF | Signal metadata format for annotated IQ file documentation | github.com/sigmf/SigMF
Protocol Analysis | SIGIDWIKI | Signal identification database with VLF examples | sigidwiki.com
Geolocation | TDOA Python lib | Time difference of arrival position estimation | github.com/AlecThomson/tdoa
Geolocation | QGIS | Open-source GIS for node position plotting | qgis.org
Graph Analysis | NetworkX | Python graph library for mesh topology and centrality | networkx.org
Fuzzing | boofuzz | Network fuzzing framework, extensible to RF | github.com/jtpereyda/boofuzz
Fuzzing | URH Fuzzer | Built-in URH fuzzing for wireless protocols | urh.readthedocs.io/en/latest/Fuzzing.html
Standards | MITRE ATT&CK for ICS | Adversary tactics and techniques for ICS environments | attack.mitre.org/matrices/ics
Standards | NIST SP 800-82r3 | ICS security guide with RF/communications coverage | nvlpubs.nist.gov/nistpubs/SpecialPublications/NIST.SP.800-82r3.pdf
Standards | IEC 62443 | Industrial cybersecurity standard series | iec.ch/iec62443
Standards | STANAG 4285 | NATO VLF/HF waveform standard | nato.int (restricted)
Standards | CISA ICS-CERT | ICS vulnerability advisories and best practices | cisa.gov/ics
Standards | FCC 47 CFR § 333 | US law prohibiting unauthorized RF jamming | law.cornell.edu/cfr/text/47/333
Timing | White Rabbit Project | Sub-nanosecond timing sync for TDOA receivers | ohwr.org/project/white-rabbit
Timing | u-blox ZED-F9T | GPS disciplined timing receiver for 1PPS sync | u-blox.com
Reporting | ATT&CK Navigator | Interactive ATT&CK matrix visualization | mitre-attack.github.io/attack-navigator
Reporting | NIST SP 800-115 | Technical guide for penetration test documentation | csrc.nist.gov/publications/detail/sp/800-115/final